## Slide 1: Gannt Chart

## Slide 2: Gantt Chart
If we were to cut the length of each post it note or card to scale and lay them out from start to finish then we basically have a Gantt Chart.
The Gantt chart is one of the project manager’s tools for scheduling

## Slide 3: The Gantt Chart - example
Time (s)
Switch stove on
Break eggs
Cook sausages
Fry eggs
Pour Water
Slice + dice salad
Get cutlery
Lay table
SLACK - SLACK - SLACK - SLACK
Place Pot on Tray
Serve
breakfast served

## Slide 4: Gantt Chart
Named after its originator Henry Gantt.
A Gantt chart is a bar graph which illustrates on a timeline when each activity will start, finish and end.
It’s a pictorial representation of each stage of the project showing individual tasks subdivided into work units according to the length of time they will take.

## Slide 5: TIME - Project Time
?
?

## Slide 6: Time – project time
The total time needed to perform a set of activities depends on 2 things:
1. DURATION – how long each activity will take,
2. SEQUENCE – the order in which you perform the activities.