## Slide 1: PROJECT EVALUATION

## Slide 2: Understanding Project Evaluation
Evaluation is the systematic and objective assessment of an on-going or completed project, its design, implementation and results.
Generally conducted by independent, external experts.
Evaluations investigate the reasons why certain aspects of a project or have or have not been implemented as planned
An evaluation should provide information that is credible and useful, enabling the incorporation of lessons learned into the decision making process
Evaluations are carried out either during the project cycle (Mid-term Evaluation, Formative Evaluation) or at the end of a project or programme (Ex-post Evaluation, Final Evaluation, Impact Evaluation, Summative Evaluation)

## Slide 3: Purpose of Project Evaluation
Learning from experience: Successes and Failures
More Transparency: by reporting to Stakeholders
Create a basis for future planning
Improved communication: foster communication and understanding within and between the stakeholders
Record Learning and share with other stakeholders
Understanding strengths & weaknesses of a project

## Slide 4: International Evaluation Principles
Objectivity: fact-based
Independence of evaluators: no intervention from staffs or other parties
Participation of all stakeholders: joint decision-making, comment on the reports
Transparency and focus: central questions, methodologies
Reliability : credibility, comprehensible
Completeness : well-structured, answer all questions
Fairness & projection of interests: dignity, security, rights must be projected
Utility: guaranteed feedback, implementation of recommendations

## Slide 5: Evaluation is most effective when…
It is a continuous not just one-off process
Involves those who are interested and answer their questions
Uses imaginative and creative approaches
Challenge discriminatory and oppressive policy of inequality
Highlights and celebrates successes and achievements
Done with honesty.

## Slide 6: Five Step Process of Evaluation
Review the Situation
Define problem
Clarify objectives
Set strategy
Gather evidence for evaluation
Establish a baseline
Set up systems for regular data (survey, forms, observation)
Analyze the evidence
Make use of the findings
Problems with external circumstances
Problems with carrying out your plans
Share findings with others
Formal/information, written/verbal
Channels of dissemination
Qualitative/Quantitative
Time limitations
Biasness
Problems with ideas

## Slide 7: Five Major Characteristics of Project Evaluation
Relevance
Effectiveness
Efficiency
Impact
Sustainability
significance of the intervention; priorities
achievement of objectives
utilization ratio of the resources
effect of the intervention to the target group
probability of long-term benefits

## Slide 8: 1. Relevance
To what extent does the intervention comply with development policy and planning of the recipient country or the partner government?
How important is the intervention for the target group and subgroups (e.g. women), and to what extent does it address their needs and interests?
To what extent do the basic principles of development policy – poverty reduction, promotion of democracy and human rights, gender equality, respect for the cultural background and ecology – correspond with the respective strategic goals and programmatic targets?

## Slide 9: 2. Effectiveness
To what extent will the objectives of the intervention be achieved?
To what extent is the target group reached?
3. Efficiency
Is the relationship between input of resources and results achieved appropriate and justifiable? What is the cost-benefit ratio?
To what extent have individual resources been used economically?
Are there any alternatives for achieving the same results with less inputs/funds?

## Slide 10: 4. Impact
What has happened as a result of the programme or project?
What real difference hast the activity made to the beneficiaries?
How many people have been affected?
Impact(s)/effects of the intervention compared to the total situation of the target group or those affected:
positive and negative, intended and unintended effects
technical, economic, social, cultural, political, ecological effects – disaggregated by sex or other relevant social groups, such as minorities

## Slide 11: 5. Sustainability
To what extent will activities, results and effects be expected to continue after donor intervention has ended?
To what extent does the intervention reflect on and take into account factors which, by experience, have a major influence on sustainability like e.g. economic, ecological, social and cultural aspects?
How self-supporting in particular is the assisted local counterpart?

## Slide 12: Challenges of Evaluation
Different persons have different expectations from an evaluation.
Some evaluations are too complex and overloaded with too many questions
A lack of interest or resistance against the evaluation
The contact between the evaluators and the employees is too close or too little.
Expectation that an evaluation will solve all problems (crisis intervention)
When the evaluation is only to legitimize the end or the continuation of a project
Lack of participation of the project stakeholders in the evaluation process
Evaluators have to write too many reports, e.g. monthly activity reports.
Evaluation results are forgotten in the daily routine of the project
Evaluation results are not taken into consideration in the next project planning

## Slide 13: Thank You